## exact name of registrant a
(Exact name of Registrant as Specified in Its Charter)
Delaware | 001-38359 | 81-3305277
(State or Other Jurisdiction of Incorporation) | (Commission File Number) | (IRS Employer Identification No.)
200 Clarendon Street Floor 6
Boston , Massachusetts |  | 2116
(Address of Principal Executive Offices) |  | (Zip Code)

## change order
Change Order
Change Order Number: 01
Project: Adicet Therapeutics 1000 Bridge Parkway Redwood City, CA 94065 | Date: 21-Sep-21 Architect's Project No: | Owner Architect | □ □
To Contractor: (Name and Address CP Construction a Division of CP Enterprises Newark, CA 94560 | Contract Date: 2 April 2021 Contract For: Tenant Improvements | Contractor Field Other | □ □ □

## change order-1
Demolition of Installed Duet
Upsizing (4) Evs
Upsize exhaust duct runs
Upsize supply duct run
Upsize (9) grilles
Subtotal | 124000
10% Profit, Overhead & Insurance | 12400
Total | 136400

## change order-2
The original Contract Sum was | 13625700
The net change by previously authorized Change Orders | 0
The Contract Sum prior to this Change Order was | 13625700
The Contract Sum will be increased by this Change Order in the amount of | 136400
The new Contract Sum including this Change Order will be | 13762100
The Contract will be unchanged by 0 days
The date of Substantial Completion as of the date of this Change Order therefore is

## until signed by the archit
UNTIL SIGNED BY THE ARCHITECT, CONTRACTOR AND OWNER.
Form4 Architecture, Inc . | CP Construct i on | Adicet Therapeutics, Inc .
ARCHITECT (Firm Name) | CONTRACTOR (Firm Name) | OWNER (Firm Name)
120 2nd St# 2. San Francisco, CA 94105 | 6662 Mayhews Landing Rd. Newark, 94560 | 200 Constitution Dr. Menlo Park, CA 94025
Address | Address | Address
/s/ Paul Ferro | /s/ Leslie Hellewell | /s/ Charlie Penner
By (Signature) | By (Signature) | By (Signature)
Paul Ferro | Leslie Hellewell | Charlie Penner
Typed Name | Typed Name | Typed Name
September 23, 2021 | September 21, 2021 | September 22, 2021
Date | Date | Date

## adicet bio inc
Adicet BIO INC
Demo | 2500
Electrical | 8000
HVAC & Plumbing | 8500
Fire Alarm | 2000
Fire Sprinklers | 3000
Frame & Drywall | 10000
Tape & Paint | 4500
Subtotal | 38500
10% Profit, Overhead & Insurance | 3850
Total | 42350

## adicet bio inc-1
The original Contract Sum was | 13625700
The net change by previously authorized Change Orders | 136400
The Contract Sum prior to this Change Order was | 13762100
The Contract Sum will be increased by this Change Order in the amount of | 42350
The new Contract Sum including this Change Order will be | 13804450
The Contract will be increased by 30 days
The date of Substantial Completion as of the date of this Change Order therefore is

## until signed by the archit-1
UNTIL SIGNED BY THE ARCHITECT, CONTRACTOR AND OWNER.
Form4 Architecture, Inc . | CP Construct i on | Adicet Therapeutics, Inc .
ARCHITECT (Firm Name) | CONTRACTOR (Firm Name) | OWNER (Firm Name)
120 2nd St# 2. San Francisco, CA 94105 | 6662 Mayhews Landing Rd. Newark, 94560 | 200 Constitution Dr. Menlo Park, CA 94025
Address | Address | Address
/s/ Paul Ferro | /s/ Leslie Hellewell | /s/ Chen Schor
By (Signature) | By (Signature) | By (Signature)
Paul Ferro | Leslie Hellewell | Chen Schor
Typed Name | Typed Name | Typed Name
March 2, 2022 | February 7, 2022 | March 18, 2022
Date | Date | Date

## adicet bio inc-2
Adicet BIO INC
Demo | 165000
Demo existing finishes & reinstall | 350000
Walls | 248815
VCT and carpet flooring | 9000
HVAC | 1662201
Electrical | 567000
Plumbing | 499644
Fire Sprinklers | 61237
Fire alarms | 47950
Doors | 151300
Lab casework, tables and lockers | 134250
Flooring labs | 134700
Equipment lift | 130000
Roofing | 45000
Structural steel | 275000
T-bar ceilings | 130320
FRP walls | 75000
Painting | 61580
Final Janitorial | 7000
General conditions & PM | 90000
Subtotal | 485017
10% Profit, Overhead & Insurance | 484501.7
Total | 5329518.7

## adicet bio inc-3
The original Contract Sum was | 13625700
The net change by previously authorized Change Orders | 178750
The Contract Sum prior to this Change Order was | 13804450
The Contract Sum will be increased by this Change Order in the amount of | 5329518.7
The new Contract Sum including this Change Order will be | 19133968.7
The Contract will be increased by see attached schedule ( ) days
The date of Substantial Completion as of the date of this Change Order therefore is

## until signed by the archit-2
UNTIL SIGNED BY THE ARCHITECT, CONTRACTOR AND OWNER.
Form4 Architecture, Inc . | CP Construct i on | Adicet Therapeutics, Inc .
ARCHITECT (Firm Name) | CONTRACTOR (Firm Name) | OWNER (Firm Name)
120 2nd St# 2. San Francisco, CA 94105 | 6662 Mayhews Landing Rd. Newark, 94560 | 200 Constitution Dr. Menlo Park, CA 94025
Address | Address | Address
/s/ Paul Ferro | /s/ Leslie Hellewell | /s/ Charlie Penner
By (Signature) | By (Signature) | By (Signature)
Paul Ferro | Leslie Hellewell | Charlie Penner
Typed Name | Typed Name | Typed Name
March 11, 2022 | March 18, 2022 | March 18, 2022
Date | Date | Date